Checklist of to dos from

3. TCA Meeting

May 15th – 18th 2006

| VENet – Model |
| --- |
| Basic VENet-graphic: Jud. will agree with Simos about the new chart as a template New model end of June, official “relaunch” in July | Aus:template –> Cyp | 08/06 |
| Regional models: house, verbal description The template is available in photoshop for everyone, the question is the additional information for outsiders, maybe it is enough for each nation to check whether the VENet model fits for the national project The Austrian VENet model will be presented in Katowice | Each partner, Aus | end of 09/06 |

| Mainstreaming |
| --- |
| National mainstreaming – info: Each partner will send information about the activities of mainstreaming that will happen or happened to Judith Reminder National Activities will be presented in Katowice | each partner, Aus | every time |
| Implementation of mainstreaming and final event | Each partner | on going |
| Newsletter / GM should be summary of GM contents of website GM contents was supposed to come from Cyprus (s. point GM), still missing, therefore NL not yet made | Aus | 08/06 |
| Leaflet 1000 copies of a nice folder have been printed and will be shared in Katowice; | Aus | end of 09/06 |

| VENet-Internet-Platform |
| --- |
| Website: Members’ access The partners will try to access the intranet and the forum of the homepage and inform Judith if it works. Judith collects all feedback for Simos. May: No access problems any more, only positive feedback | Each partner, Aus | end of 05/06 |
| Link list reg. GM Several reminders Received some links with GM cartoons end of August | Cyp ( Aus | end of 05/06 |
| Uploads: Judith will upload TCA-documents on download-section 23.05.: upload of docs | Aus | mid of 06/06 |
| Target group/website: Judith will send a list to think about concerning the target groups on the website to everyone; the answers will be compiled by Judith and put on the website 24.05.: Judith sent document with first suggestions to all 20.06.: reminder to all 26.07.: Official relaunch incl. section with target groups | Jud. ( all / everyone ( Jud. | end of 07/06 |
| Julia will clarify the point of technical web support with the Youth Board of Cyprus and will inform the others 05-07:No official clarification, but technical support worked well Judith checked with Simos: Hosting and support agreed until Sept. 07 | Cyp | end of 09/06 |

| Support System |
| --- |
| Content: Make your VENet 06.06.: Doc from Piotr 21.06.: Comment from Peter 06.07.: Proof read by native speaker 10.07.: New Layout put on website in July | Ger, Pld | end of 05/06 |
| Content: Info about Support System 06.06.: Doc from Piotr 21.06.: Comment from Peter 06.07.: Proof read by native speaker put on website in July | Pld | 9th 06/06 |
| Button frontpage “Make your VENet” will be installed by Simos on the homepage done in June | Aus, Cyp | mid of 06/06 |
| Proposal for toolbox-structure Will be presented in Katowice? | Pld | end of 09/06 |
| Gender Mainstreaming |
| Button website „GM“ + content 22.05. Diversity policy from Apanemi 22.06. Suggestions for GM contents from Judith to Julia 18., 25.07. reminder After many reminders and a prepared concept from Judith, a draft of the introduction came in September (and it still is a draft…) | Cyp, Aus | end of 07/06 |
| Miscellaneous |
| Help for Cypriot DP: Julia will make an abstract about the problem concerning the Cypriot DP and will send this to each VENet partner with suggestions of support from other partners. VENet partners will give feedback about their possibilities of support and help. Nothing received from Julia | Julia – each partner |  |

- Most to dos completed

- GM contents for website and Newsletter not done

- Some topics will be presented in the meeting (national VENet Models, tool box)

- Some delays but with no big relevance to the project progress, except that cooperation with Cyprus is fairly time and energy consuming